## Sheet1
Version dated 26 November 2024- KDK | Note pre 2024: the PDGHAD and H&A have completed, submitted and SCC approved As required under SCC Grading permit #83-1194 (1983-closed when state park located rock removed).
| 2024 | [7 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
ACTIVITIES | MAY | JUNE | JULY | AUG. | SEPT. | OCT. | NOV. | DEC. | JAN. | FEB. | MAR. | APR. | MAY | JUNE | JULY | AUG. | SEPT. | OCT. | NOV. | DEC. | JAN. | FEB. | MAR. | APR. | MAY | JUNE | JULY | AUG. | SEPT. | OCT. | NOV. | DEC. | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
A) PERMITTING 2023-2024
Funding Approval from PDGHAD |  |  |  | Funding Vote Passed
Formalize Conditional Permit #231411-per#231411 Sect I-subpart A | PDGHAD-Sign | SCC Planning-Sign | Condition "A" complete
Submit/Obtain a Discretionary Level 3 Grading Permit to include Environmental Review & CEQA analysis FROM SCC Environmental coordinator-per#231411 Sect I-subpart B |  |  | Q for JD-unclear how soon can we do this?- year of construction? Assume results filled w/ condition E? | [19 empty] | Condition "B" complete
Submit an Updated Biotic Report for SCC Biologist review-per#231411 Sect. I-subpart C | [10 empty] | GHAD hired bio on-site | H&A Draft to GHAD | Draft to SCC | SCC Biologist-Sign | Condition "C" complete
Geotechnical Report-per#231411 Sect. I-subpart D | [7 empty] | H&A Draft to GHAD | Draft to SCC | SCC Engineer-Sign | Condition "D" complete
Submit/Obtain Stand Alone Grading Permit from SCC Building Official-per#231411 Sect I-subpart E | [8 empty] | Q fdor JD-unclear how soon we can do this?- year of construction? Assume once signed have 180 days to start the work? | [13 empty] | Condition "E" complete?
Obtain an Encroachment Permit from CA Dept. State Parks-per#231411 Sect I-subpart F | PDGHAD-Start |  | Draft to SCC | Condition "F" complete
Snowy Plover Nesting Season | X | X | X | X |  |  |  |  | X | X | X | [5 empty] | X | X | X | X | X | X | X | [5 empty] | X | X | X | X | X |  | Sept 1st | X | X |  | Sept 1st | X | X |  | Sept 1st | X | X |  | Sept 1st | X
B) PRE-CONSTRUCTION | [22 empty] | No additional permits/ work by PDGHAD is planned until the 3-year duration of post- construction observation is complete
100% Plans For Construction-for Rock Revtement Repair & PDGHAD/H&A Work Plan-per#231411 Sect II-subpart A | [9 empty] | H&A /Contractor Draft to GHAD | Draft to SCC | SCC Engineer-Sign | Condition complete
RFP/contracting |  | X- H&A | X-Bio? |  |  | X- Contractor
Get written confirmation from U.S. Fish & Wildlife-per#231411 Mitigation Bio-1 |  |  | GHAD hired bio on-site | [10 empty] | GHAD hired bio on-site ? | SCC Biologist-Sign | "Mitigation Bio-1" complete
Qualified Biologist, on-site for initial construction, monitor progress for a minimum of 3yrs-per#231411 Mitigation Bio-2 through -5. | [16 empty] | GHAD hired bio on-site- part time? | GHAD hired bio on-site- part time? | GHAD hired bio on-site- part time? | [6 empty] | GHAD hired bio on-site ? | Draft to GHAD | Draft to SCC | SCC Biologist-Sign |  |  |  |  | GHAD hired bio on-site* | Draft to GHAD | SCC Biologist-Sign |  | GHAD hired bio on-site* | Draft to GHAD | SCC Biologist-Sign |  | GHAD hired bio on-site* | Draft to GHAD | SCC Biologist-Sign | "Mitigation Bio-3-5" complete
Pre-construction survey of Property (H&A) | [12 empty] | GHAD-Notify residents/ access | H&A On-site* | H&A On-site | H&A report to GHAD
Pre-construction access/clearance (create laydown yard & Fence off sensitive areas) | [15 empty] | All Contractor kick-off
Shoring Plans- reviewed 2weeks prior to construction by County | [14 empty] | PDGHAD-Submitt | SCC Engineer-Sign | Condition complete
Submit/Obtain Stand Alone SCC Building Permit for Stairs removal & rebuild (7) | [14 empty] | PDGHAD-Submitt | SCC Engineer-Sign |  |  |  | Condition complete
C) CONSTRUCTION
Pre-con Kick Off | [16 empty] | X | X | X
Remove stairs as go, Replace once all rock replacement complete. Or as we go? | [16 empty] | X | X | X
Revetment Repair | [16 empty] | X | X | X
CM- of Revetment repair (H&A?) | [16 empty] | H&A On-site | H&A On-site | H&A On-site
D) POST-CONSTRUCTION
Post-construction survey of Property (H&A) | [18 empty] | GHAD-Notify residents/ access | H&A On-site* | H&A On-site | H&A report to GHAD
H&A Final Construction Report*
(https://sccoplanning.com/Portals/2/County/Planning/bldg/Consultant%20Final%20Inspection_PLG305.pdf) Submit completed "Final Inspection" form PLG305 | [20 empty] | Contractor close out to GHAD | SCC Engineer-Sign | Condition complete
E) Non-rock revetement plan: Standard O&M Activities for reference ONLY (Part of H&A annual budget of XX)
Annual Inspection & Report |  | H&A on-site | [11 empty] | H&A On-site* | [12 empty] | H&A On-site* | [6 empty] | H&A On-site* | Draft to GHAD | Final to SCC |  | H&A On-site* | Draft to GHAD | Final to SCC |  | H&A On-site* | Draft to GHAD | Final to SCC |  |  |  | Final to SCC
Updating O&M Manual | [26 empty] | H&A draft to GHAD | Draft to GHAD | Final for SCC files |  |  |  | 2030 Q1: H&A draft to GHAD; 2030 Q2: Draft to GHAD; 2030 Q3: Final for SCC files
Additional Support per PDGHAD requests
Abbreviations Legend: |  |  | The above schedule for items B and C is preliminary and assumes no delays in agency reviews, permitting, and field and/or funding constraints. Scope and schedules should be modified if additional information or technical constraints are identified during investigations.
Indicates task occurs within this month/timeframe as marked | X
Annual Inspection | AI
Santa Cruz County | SCC
Pajaro Dunes Geologic Hazard Abatement District | PDGHAD
Conditional Permit- Staff Report & Preliminary Grading Permit Level 3-Administrative Review (Application #231411) | Conditional Permit #231411
Pink highlight- Condition required by permit | Green highlight | Approval from SCC- Conditions or permit closed out
Red text | Indicates close out activity
Indicates integrated scope/activities | *
Blue highlight | Approval from PDGHAD
Yellow highlight | Deliverable to SCC
Grey highlight | Plover Nesting Season (March 1st through September 1st-if nestss w/ fledglings present w/in 1,000ft)
Orange highlight | On-site Activity
KDK Notes of steps
| https://tidesandcurrents.noaa.gov/noaatidepredictions.html?id=9413450&legacy=1 | tidal info
Conditional Permit #231411
Funding Approval from PDGHAD
Santa Cruz County (SCC) Permits
SCC Building Permit for Stairs removal & rebuild (7)
Fish & Wildlife & SCC Biologist Review
Santa Cruz County Field Inspections
Santa Cruz County Permit Close outs
Santa Cruz County Final Clear all Permits as closed (even the original 1983!)